## DR5-7 documents
Sr. # | NPD Task Deliverable | Document ID | Document template | Author | Resp | Document completion traget date | Internal Quality Review | Indepdent review | Document to release by | Status | Remarks
1 | Manufacturing/Design Transfer Plan (MDTP) | Not applicable | D0000000222 Design Transfer Plan |  | - | NA | - | - | - | - | Document not eapplicable supplier own mfg process
2 | Design transfer checklist | D001020027 | SGTC-QFM-DLC-004-03 |  | Salman | 18/02/2022 |  |  | DR5
3 | Design Transfer Readiness Tool vAB | To assign | D0000000221 |  | Vikram | 18/02/2022 |  |  | DR7 |  | DR1-4 document planned in DR5
4 | Mfg transfer | TBC | CQF-SUP-017-A |  | Vikram | 18/02/2022 |  |  | DR7 |  | Format to recehck as not available in Coporate procedure, This is obsolete form
5 | AO Lessons Learned vAB_clean | TBC | D0000000224 |  | Vikram | 18/02/2022 |  |  | DR7 |  | DR1-4 document planned in DR5 To check with SGTC QA if we need to provdie leranings from project to update in central document owned by SGTC team or it will be individual document for project
6 | Process design concept (iteration & experimentation) | D001020012 | D0000000220, Process Assessment Tool vAB | SFO | Vikram | 18/02/2022 |  |  | DR5 |  | Supplier document
7 | Device specification DMR | D001020045 | D0000000223 DMR Checklist vAB_clean |  | Vinod | 18/02/2022 |  |  | DR6 / DR7
8 | DIOV-DIOTV | D001020006 | DIOV template DR1-4 to update further |  | Salman | 18/02/2022 |  |  | DR7
9 | CQA | D001020084 | List of CQA |  | Salman | 18/02/2022 |  |  | DR6
10 | Supplier Management specifications [DMR document] | D001020045, Document # To assign | Approved supplier list Supplier Agreements (QAA/Change control) document to include in DMR checklist D0000000223 D0000000209 (PPAP) |  | Vipin | 18/02/2022 |  |  | DR7 |  | For PPAP VIkram
11 | Product Security Risk Table | D001020017 | Product security risk table D0000000909 |  | Deepak | 18/02/2022 |  |  | DR7 |  | DR1-4 document planned in DR5 | TBC with Deepak
12 | Product Security Standard Assessment | D001020014 | D0000003422 |  | Deepak | 18/02/2022 |  |  | DR7 |  | DR1-4 document planned in DR5
13 | PFMEA | To assign | SGTC-QFM-DLC-022-01 | SFO | Vikram | 18/02/2022 |  |  | DR6 |  | DR1-4 document planned in DR5 Supplier documents and applicable
14 | PCP | To assign | SGTC-QFM-DLC-021-01 | SFO | Vikram | 18/02/2022 |  |  | DR6 |  | DR1-4 document planned in DR5
15 | PPAP | To assign | D0000000209 (PPAP) |  |  | 18/02/2022
16 | Labeling Specifications [DMR document] IFU/Product Label/Shipping Label | Product Label and Shipping Label will be Drawing number IFU: Part Number | IFU reference SGTC format Labels in drawing format to release & update in DMR document # D001020045 |  | Vikram | 18/02/2022 |  |  | DR7 |  | Stryker released document
17 | Packaging Specifications [DMR document] | Packaging Drawings number will be added in DMR specification document D0010220045 | Packaginf drawing & specification to update in DMR document # D001020045 SGTC-QFM-DLC-008-12 & Pacaging Design drawings - SGTC comment Document number SGTC-QFM-DLC-008-12 will be replaced with D0000000223 |  | Vikram | 18/02/2022 |  |  | DR7 |  | Stryker released document
18 | Production (Manufacturing) process specifications [DMR document] | D001020045 | Supplier documents referenced in DMR checklist D0000000223 | SFO | Vikram | 18/02/2022 |  |  | DR7 |  | Stryker released document
19 | Labeling process specifications [DMR document] | D001020045 | Supplier documents referenced in DMR checklist D0000000223 | SFO | Vikram | 18/02/2022 |  |  | DR7 |  | Stryker released document
20 | Packaging process specifications [DMR document] | D001020093 Packaging Procedure | Packaging Procedure to update in DMR sheet D0000000223 |  | Vikram | 18/02/2022 |  |  | DR7 |  | Stryker released document
21 | Installation process specifications [DMR document] | D001020092: Installation Manual | Installation Manual to update in DMR checklist D0000000223 |  | Salman | 18/02/2022 |  |  | DR7
22 | Servicing process specifications [DMR document] | D001020045 Service plan / Manual doc # TBA | Document # to update in DMR checklist D0000000223 |  | TBC | 18/02/2022 |  |  | DR7 |  | To be planned in DR8 stage
23 | Reprocessing specifications [DMR document] | - | - |  | - | NA |  |  | - | NR | Will be part of service document
24 | Process Quality Assurance specifications (Inspection & Test) [DMR document] | D001020045 | Supplier documents referenced in DMR checklist D0000000223 | SFO | Vikram | 18/02/2022 |  |  | DR7
25 | Software Detailed Design Display Unit | D001020039 | SGTC-QFM-DLC-001-07 | TM | Dushyant | 18/02/2022 |  |  | DR5 |  | DR1-4 document planned in DR5
26 | URS review checklist | D001020042 | SGTC-QFM-DLC-001-23 |  | Ketan | 18/02/2022 |  |  | DR5 |  | DR1-4 document planned in DR5
27 | Hardware Design Document - Display unit | D001020076 | - | TM | Chetan | 18/02/2022 |  |  | DR5 |  | DR1-4 document planned in DR5
28 | Hardware Design Document - Sub CPU (Slave) Board | D001020077 | - | SFO | Chetan | 18/02/2022 |  |  | DR5 |  | DR1-4 document planned in DR5
29 | SRS review checklist Nurse station (Cloud) | D001020027 | SGTC-QFM-DLC-001-03 | GTL | Deepak | 18/02/2022 |  |  | DR5 |  | DR1-4 document planned in DR5
30 | SRS review checklist Tablet | D001020028 | SGTC-QFM-DLC-001-03 | GTL | Deepak | 18/02/2022 |  |  | DR5 |  | DR1-4 document planned in DR5
31 | SRS review checklist Display Unit | D001020029 | SGTC-QFM-DLC-001-03 | TM | Dushyant | 18/02/2022 |  |  | DR5 |  | DR1-4 document planned in DR5
32 | SRS review checklist Slave boards | D001020030 | SGTC-QFM-DLC-001-03 | SFO | Dushyant | 18/02/2022 |  |  | DR5 |  | DR1-4 document planned in DR5
33 | SAD review checklist Nurse station (Cloud) | D001020035 | SGTC-QFM-DLC-001-04 | GTL | Deepak | 18/02/2022 |  |  | DR5 |  | DR1-4 document planned in DR5
34 | SAD review checklist Tablet | D001020036 | SGTC-QFM-DLC-001-04 | GTL | Deepak | 18/02/2022 |  |  | DR5 |  | DR1-4 document planned in DR5
35 | SAD review checklist Display Unit | D001020037 | SGTC-QFM-DLC-001-04 | TM | Dushyant | 18/02/2022 |  |  | DR5 |  | DR1-4 document planned in DR5
36 | SAD review checklist Slave boards | D001020038 | SGTC-QFM-DLC-001-04 | SFO | Dushyant | 18/02/2022 |  |  | DR5 |  | DR1-4 document planned in DR5
37 | SDD review checklist Tablet | D001020043 | SGTC-QFM-DLC-001-07 | GTL | Deepak | 18/02/2022 |  |  | DR5 |  | DR1-4 document planned in DR5
38 | SDD review checklist Display Unit | D001020044 | SGTC-QFM-DLC-001-07 | TM | Dushyant | 18/02/2022 |  |  | DR5 |  | DR1-4 document planned in DR5
39 | SDD review checklist Slave boards | D001020045 | SGTC-QFM-DLC-001-07 | SFO | Dushyant | 18/02/2022 |  |  | DR5 |  | DR1-4 document planned in DR5
40 | Software Architect Diagram (System level) | D001020080 | SGTC-QFM-DLC-001-05 |  | Dushyant | 18/02/2022 |  |  | DR5 |  | DR1-4 document planned in DR5
41 | Traceability Matrix Display unit | D001020060 | SGTC-QFM-DLC-001-08 | TM | Dushyant + Chetan | 18/02/2022 |  |  | DR6 |  | New document (Requirement to include - Electrical + Software)
42 | Traceability Matrix Slave boards | D001020061 | SGTC-QFM-DLC-001-08 | SFO | Dushyant + Chetan | 18/02/2022 |  |  | DR6 |  | CPT document update – Copy old document content and create new document (Requirement to include Electrical + Software)
43 | Traceability Matrix Nurse station | D001020062 | SGTC-QFM-DLC-001-08 | GTL | Deepak | 18/02/2022 |  |  | DR6 |  | CPT Document update
44 | Traceability Matrix Tablet | D001020063 | SGTC-QFM-DLC-001-08 | GTL | Deepak | 18/02/2022 |  |  | DR6 |  | New document - Copy old document content and create new document
45 | Unit Test Nurse Station (Cloud) | D001020046 | SGTC-QFM-DLC-001-12 | GTL | Deepak | 18/02/2022 |  |  | DR7 |  | New document TBC
46 | Unit Test Tablet | D001020047 | SGTC-QFM-DLC-001-12 | GTL | Deepak | 18/02/2022 |  |  | DR7 |  | New document
47 | Unit Test Display unit | D001020048 | SGTC-QFM-DLC-001-12 | TM | Dushyant | 18/02/2022 |  |  | DR7 |  | New document
48 | Unit Test Slave boards | D001020049 | SGTC-QFM-DLC-001-12 | SFO | Dushyant | 18/02/2022 |  |  | DR7 |  | New document
49 | Integration Test Nurse Station (Cloud) | D001020050 | SGTC-QFM-DLC-001-15 | GTL | Ashish (Deepak) | 18/02/2022 |  |  | DR7 |  | CPT update to update | Int test case there will be single document
50 | Integration Test Tablet | D001020051 | SGTC-QFM-DLC-001-15 | GTL | Ashish (Deepak) | 18/02/2022 |  |  | DR7 |  | New document
51 | Integration Test Display unit | D001020052 | SGTC-QFM-DLC-001-15 | TM | Pragya | 18/02/2022 |  |  | DR7 |  | New document
52 | Integration Test Slave boards | D001020053 | SGTC-QFM-DLC-001-15 | SFO | Pragya | 18/02/2022 |  |  | DR7 |  | CPT update to update
53 | System Test | D001020058 | SGTC-QFM-DLC-001-21 |  | Pragya + Ashish + Gaurav | 18/02/2022 |  |  | DR7 |  | New document (Requirement to include Software + Electrical + Firmware combined document) | DIOV requirement to cover in system test
54 | Source code checklist Nurse Station (Cloud) | D001020068 | SGTC-QFM-DLC-001-20 | GTL | Deepak | 18/02/2022 |  |  | DR7 |  | New document
55 | Source code checklist Tablet | D001020069 | SGTC-QFM-DLC-001-20 | GTL | Deepak | 18/02/2022 |  |  | DR7 |  | New document
56 | Source code checklist Display unit | D001020070 | SGTC-QFM-DLC-001-20 | TM | Dushyant | 18/02/2022 |  |  | DR7 |  | New document
57 | Source code checklist Slave boards | D001020071 | SGTC-QFM-DLC-001-20 | SFO | Dushyant | 18/02/2022 |  |  | DR7 |  | New document
58 | Software Release note Nurse Station (Cloud) | D001020072 | SGTC-QFM-DLC-001-25 | GTL | Deepak | 18/02/2022 |  |  | DR7 |  | New document
59 | Software Release note Tablet | D001020073 | SGTC-QFM-DLC-001-25 | GTL | Deepak | 18/02/2022 |  |  | DR7 |  | New document
60 | Software Release note Display unit | D001020074 | SGTC-QFM-DLC-001-25 | TM | Dushyant | 18/02/2022 |  |  | DR7 |  | New document
61 | Software Release note Slave boards | D001020075 | SGTC-QFM-DLC-001-25 | SFO | Dushyant | 18/02/2022 |  |  | DR7 |  | New document
62 | Integration verification checklist | D001020081 | SGTC-QFM-DLC-001-13 | TM SFO | Pragya + Ashish | 18/02/2022 |  |  | DR7 |  | To confirm with team ( Slaveboards + Display ) separate
63 | Risk Table | D001020010 | DIOV template DR1-4 to update further till column 13 |  | Vinod | 18/02/2022 |  |  | DR7
64 | Usability Engineering Formative evaluations | D001020008 | Formative evaluation plan for usability |  | Ketan | 18/02/2022 |  |  | DR6
65 | Design verification and Validation Design verification and Validation Plans Design verification and Validation Protocols | D001020049 Plan D001020082 - Protocol D001020083- Reports | SGTC-QFM-DLC-006-03:Plan SGTC-QFM-DLC-006-01:Protocol SGTC-QFM-DLC-006-02:Report |  | Gaurav | 18/02/2022 |  |  | DR6
66 | Labeling Review | - | Peer review |  | Vikram | NA |  |  | DR6 |  | Peer review inputs will be added in Design Review 5-7.
67 | Packaging Review | - | Peer review |  | Vikram | NA |  |  | DR6 |  | Peer review inputs will be added in Design Review 5-7.
68 | Handling, Storage, & Distribution Review | - | Peer review |  | Vipin | NA |  |  | DR6 |  | Peer review inputs will be added in Design Review 5-7.
69 | Installation Review | - | Peer review |  | Vikram | NA |  |  | DR6 |  | Peer review inputs will be added in Design Review 5-7.
70 | Servicing Review | - | Peer review |  | TBC | NA |  |  | DR6 |  | Peer review inputs will be added in Design Review 5-7.
71 | Process Verification & Validation at Stryker | TBC | TBC |  | Vikram | NA |  |  | DR7 |  | Applicable only if process owned by Stryker e.g. Label printing etc
72 | Product & Process Freeze Review | - | Peer review |  | Peer review integrated with Design review 1-4 | NA |  |  | DR5 |  | Peer review integrated with Design review 1-4, Planned in DR5 | TBC how to closre in DR
73 | Process Verification & Validation at Suppliers | D001020045 | Supplier's process validation documents, D0000000209 PPAP | SFO | Vikram | 18/02/2022 |  |  | DR7 |  | Supplier document to referenced in DMR
74 | Design Review 5-7 | D001020046 | SGTC-QFM-DLC-002-09 |  | Vikram | 18/02/2022 |  |  | DR7 |  | Design review to be initiated only after DR5-7 document release completion
75 | Software Development Plan (Display Unit + Slave boards Firmware + Hardware) | D001020021 | SGTC-QFM-DLC-001-01 | TM | Dushyant | 18/02/2022 |  |  | DR 4 |  | DR1-4 document pending for closure
76 | SmartMedic_Phase II Cloud-Nurse Station SOFTWARE_ARCHITECTURE_DESIGN | D001020031 | SGTC-QFM-DLC-001-04 | GTL | Deepak Sharma | 18/02/2022 |  |  | DR 4 |  | DR1-4 document pending for closure
77 | SmartMedic_TabletApp-SOFTWARE_ARCHITECTURE_DESIGN | D001020032 | SGTC-QFM-DLC-001-04 | GTL | Deepak Sharma | 18/02/2022 |  |  | DR 4 |  | DR1-4 document pending for closure
78 | Software Development Plan (Nurse station Cloud, Tablet) SmartMedic Phase II | D001020020 | SGTC-QFM-DLC-001-01 | GTL | Deepak Sharma | 18/02/2022 |  |  | DR 4 |  | DR1-4 document pending for closure
79 | SmartMedic_NurseStattion_SOFTWARE_REQUIREMENTS_SPECIFICATION | D001020023 | SGTC-QFM-DLC-001-02 | GTL | Deepak Sharma | 18/02/2022 |  |  | DR 4 |  | DR1-4 document pending for closure
80 | SmartMedic_TabletApp-SOFTWARE_REQUIREMENTS_SPECIFICATION | D001020024 | SGTC-QFM-DLC-001-02 | GTL | Deepak Sharma | 18/02/2022 |  |  | DR 4 |  | DR1-4 document pending for closure
81 | Software Requirements Specification Display Unit | D001020025 | SGTC-QFM-DLC-001-02 | TM | Chetan Sanghvi | 18/02/2022 |  |  | DR 4 |  | DR1-4 document pending for closure
82 | Software Architecture Design Display Unit | D001020033 | SGTC-QFM-DLC-001-04 | TM | Chetan Sanghvi | 18/02/2022 |  |  | DR 4 |  | DR1-4 document pending for closure
83 | Software Detailed Design Slave boards | D001020041 | SGTC-QFM-DLC-001-06 | SFO | Chetan Sanghvi | 18/02/2022 |  |  | DR 4 |  | DR1-4 document pending for closure
84 | Software Requirements Specification Slave boards | D001020026 | SGTC-QFM-DLC-001-02 | SFO | Chetan Sanghvi | 18/02/2022 |  |  | DR 4 |  | DR1-4 document pending for closure
85 | Software Architecture Design Slave boards | D001020034 | SGTC-QFM-DLC-001-04 | SFO | Chetan Sanghvi | 18/02/2022 |  |  | DR 4 |  | DR1-4 document pending for closure
86 | Software Detailed Design Display Unit | D001020040 | SGTC-QFM-DLC-001-06 | TM | Chetan Sanghvi | 18/02/2022 |  |  | DR 5 |  | DR1-4 document Planned in DR5
87 | Requirements for Product Label | D001020085 | SGTC-QFM- DLC-011-01 |  | Vinod / Salman | 18/02/2022 |  |  | DR5-7 |  |  | TBC if mandatory
88 | Requirements for Packaging Label | D001020086 | SGTC-QFM- DLC-011-02 |  | Vinod / Salman | 18/02/2022 |  |  | DR5-7 |  |  | TBC if mandatory
89 | Requirementsfor IFU | D001020087 | SGTC-QFM- DLC-011-03 |  | Vinod / Salman | 18/02/2022 |  |  | DR5-7 |  |  | TBC if mandatory
90 | Literature Review Checklist | D001020088 | SGTC-QFM-DLC-008-17 |  | Vinod / Salman | 18/02/2022 |  |  | DR5-7 |  |  | TBC if mandatory
91 | Serviceability Plan | D001020089 | SGTC-QFM-DLC-008-10 |  | TBC | 18/02/2022 |  |  | DR5-7 |  |  | TBC if mandatory
92 | Quality inspection plan | D001020090 | SGTC-QFM-DLC-008-11 |  | Vinod / Vikram | 18/02/2022 |  |  | DR5-7 |  |  | TBC Inspec of product after receipt at SGTC
93 | Product Release form | D001020091 | SGTC-QFM-DLC-008-19 |  | Vikram | 18/02/2022 |  |  | DR5-7
94 | Customer visit report | TBA | SGTC-QFM-DLC-008-25 |  | Kuldeep | 18/02/2022 |  |  | DR5-7